## Sheet1
Level | Room | Area | Area Code | Full Code | Batch | Batch Code | Handover | Handover Date | Stage 1 Completion Date | Stage 2 Completion Date | Stage 3 Completion Date | Stage 4 Completion Date | Stage 5 Completion Date | Works | Status | Room Completion Date
01 | Kitchen | A | 00 | 01-01-00 | 1 | 01-1 | Yes | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | Completed | Completed | 2020-03-02
01 | Bedroom | A | 00 | 01-02-00 | 1 | 01-1 | Yes | 2020-01-20: 2020-01-20; 2020-01-27: 2020-01-27 | Civil works in progress | In Progress
01 | Bathroom | B | 01 | 01-01-01 | 1 | 01-1 | Yes | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | Completed | Completed | 2020-03-02
01 | Bedroom | B | 01 | 01-02-01 | 1 | 01-1 | Yes | 2020-01-20: 2020-01-20; 2020-01-27: 2020-01-27 | Civil works in progress | In Progress
01 | Closet | B | 01 | 01-03-01 | 1 | 01-1 | No | [6 empty] | No yet constructed | No yet constructed
01 | Dinning | C | 02 | 01-01-02 | 1 | 01-1 | Yes | 2020-01-06 | 2020-01-16 | 2020-01-23 | 2020-01-30 | 2020-02-06 | 2020-02-13 | Completed | Completed | 2020-03-02
01 | laundry | C | 02 | 01-02-02 | 1 | 01-1 | Yes | 2020-01-06: 2020-01-06; 2020-01-16: 2020-01-14 | Civil works in progress | In Progress
01 | Living Room | C | 02 | 01-03-02 | 1 | 01-1 | Yes | 2020-01-06 | 2020-01-15 | 2020-01-22 | 2020-01-29 | 2020-02-05 | 2020-02-12 | Completed | Completed | 2020-03-02
01 | Master bath | D | 03 | 01-01-03 | 1 | 01-1 | Yes | 2020-01-06: 2020-01-13; 2020-01-15: 2020-01-20 | Civil works in progress | In Progress
01 | Master Bedroom | D | 03 | 01-02-03 | 1 | 01-1 | Yes | 2020-01-06: 2020-01-13; 2020-01-15: 2020-01-20 | Civil works in progress | In Progress
01 | Rest Area | E | 04 | 01-01-04 | 1 | 01-1 | Yes | 2020-01-06: 2020-01-13; 2020-01-15: 2020-01-20 | Civil works in progress | In Progress